## Slide 1: Creating Road Maps
Checking our thinking
Notes: *Note: This presentation can be shortened to focus on the following pages: 1, 2, 6, 8, 12, 15, 17, 26, 37, 39
Making Result chains is a really important part of deciding and showing others where you are going with your work.
It also helps you to check if you will reach your destination (goals).
They can take a bit of thinking, but work well as a tool.
Other terms for Result chains are ‘road maps’ or ‘theory of change’

## Slide 2
Deciding what the plan is about
Making the plan
Doing and monitoring the work
Deciding if the plan is working
Telling ourselves and others
Goals
Strategies
Road Maps
Measures
In the Conservation Standards “Roadmaps” refers to “Results Chains”
Notes: Making Result chains is a really key part of the ‘Making the Plan’ step, and brings a lot of our thinking together
From here we can confidently go into the measures and Doing the Work

## Slide 3
Notes: This cartoon really tells the story about why we need a result chain.
A lot of projects are not very clear about how the work they are going to do will lead to the goals they have set.
They assume that ‘A miracle’ will occur that will make their project work.
We use the result chains to find where we think a miracle will occur and then figure out a way to deal with that.

## Slide 4
What are road maps / result chains?
The main parts of road maps
Creating road maps
Group exercises
Using road maps
Making the Plan
Road Maps
Overview presentation

## Slide 5
What is a Road Map / Result chain?
A diagram we create to help us work out if our Strategies are likely to have the effect we thought they would
Like a road map – so we can call them that instead
Contains a series of “if…then” causal statements
Making the Plan
Road Maps
Linking strategies and actions to outcomes
Notes: We want to introduce the concept of results chains.
What is a Results Chain?
It is a simple tool that clarifies the assumptions about how strategies contribute to reducing threats and achieving the health of targets.

## Slide 6
Why we do this step?
  To be confident that the Strategies we have chosen will get the result that we want
  To be clear about the tasks / monitoring we have to do
  Because we want to see results, not just effort
Making the Plan
Road Maps
Linking strategies and actions to outcomes
Notes: The hardest thing for people new to doing results chains is thinking in terms of results and not activities.
We need to do activities of course – if we don’t do stuff then stuff wont change
But we want to be able to show what results come when we do stuff, because results are what we want
For example, we don’t do weed control just because we like controlling weeds (most people anyway) but because we want to see healthier rivers or better fire.
Thinking about the results we want helps us think about the work we need to do

## Slide 7
Notes: Here is a real-life example from Central Australia
It says that we implement a Strategy (light fires to burn the country)
We expect to get a result of ‘grass is going to come back’
If we get that result than ‘all the animals will come back’
If we get that result then ‘hill kangaroo and rock wallabies’ can come back
And if we get that result then ‘old people go out hunting and will feel happy’ – our Target.

## Slide 8
TODAY
TOMORROW
Targets
Threats
Situation
Dream
Target Goals
Threat Goals
Strategies
Actions
Measures
Reporting
Making the Plan
Road Maps
Recap – what is planning
Road Map
Notes: We have talked before about ‘What is planning’ being a way to move from where we are Today to where we want to be Tomorrow.
We make result chains to join those things up – they help to make sure the Strategies and Actions will get us from Today to Tomorrow.

## Slide 9
Like a road map for your work
Helps to show the way the things you do are connected to the result you want to see
Helps build your workplan and your monitoring plan
Making the Plan
Road Maps
Linking strategies and actions to goals
Notes: A good way to help think about the difference between Activities and Results, and the idea of a Result Chain as a Roadmap is to use an example of travelling between two places.
You can substitute a local example if you wish, which will make it more locally relevant.

## Slide 10
JABIRU
DARWIN
By 5pm
South Alligator
Bark Hut
Corroboree
Humpty Doo
By 4pm
By 3pm
By 2pm
By 1pm
By Midday
Get Vehicle
Get Fuel
Drive for an hour
Drive for an hour
Drive for an hour
Get an icecream
Drive for an hour
Drive for an hour
RESULTS
ACTIVITIES
Notes: This slide ‘builds’ through a series of animations, first the LHS, then the RHS, and finally the two headings.
What we are doing is showing that when we go on a journey between two places we are interested in the result (did I get to my destination) and we can check our progress as we go by looking at signs along the way (eg if I see the sign to Corroboree I know I am on the right road to my destination of Jabiru).
But, I was to just focus on the activities, all I know is that I have driven for 2 hours, and I need to drive for 3 more, but I don’t know if I am where I need to be until 5 hours have passed.
I could be anywhere that is 5 hours from my starting point if I don’t think about results (towns / signposts), and only think about activities (driving).
It is the same with our projects – we very often concentrate on the RHS, but we really need to be concentrating on the LHS because that tells us about progress.

## Slide 11
JABIRU 
DARWIN
By 5pm
South Alligator
Bark Hut
Corroboree
Humpty Doo
By 4pm
By 3pm
By 2pm
By 1pm
By Midday
RESULTS
Notes: This slide just shows the LHS by itself.

## Slide 12
DARWIN
Get Vehicle
Get Fuel
Drive for an hour
Drive for an hour
Drive for an hour
Get an icecream
Drive for an hour
Drive for an hour
ACTIVITIES
JABIRU ?
Notes: This slide just shows the RHS by itself.

## Slide 13
Making the Plan
Results chains
Linking strategies and actions to goals
Notes: Just another way of visualizing the idea of a Roadmap

## Slide 14
What are road maps / result chains?
The main parts of road map
Creating road maps
Group exercises
Using road maps
Making the Plan
Road Maps
Overview presentation

## Slide 15
Making the Plan
Road Maps
The Basic Components of a Road Map / Results Chain
Strategy
Result
Result
Target
Impact of Actions achieves/maintains Health
Threat
Goal
achieved
Indirect
Threat
abated or
opportunity seized
Result
Indirect
Threat
abated or
opportunity seized
Notes: Here we are seeing the main parts of a result chain (or roadmap) as they appear in Miradi
Moving from Left (Strategy) to Right (Target) through a set of results
Actual chains might be longer, but they will have this layout.

## Slide 16
Making the Plan
Road maps
Program logic / MERI by another name
Notes: Some people will have used approaches such as Program Logic
A result chain is just another form of Program Logic

## Slide 17
Threat Goal: To reduce by 75% the consumption of fuel wood collected from biologically sensitive forests in the project area in 10 years
Strategy
Result
Result
Threat reduction result
Making the Plan
Road Maps
Simple example
Outreach efforts & install alternative energy devices
Switch to efficient heating and cooking devices
Reduce burning of fuelwood
Reduce logging
Forests
Notes: Here is an example from NW Yunnan in China, where they developed an ambitious objective of reducing by 75% the consumption of fuel wood collected from biologically sensitive forests in the project area in 10 years
The simplified results chain to support this strategy is indicated in the diagram

## Slide 18
Making the Plan
Road Maps
Example of project Road Map / Result chain
Notes: Here is another example – this one comes from the Marine example project that is in Miradi

## Slide 19
What are road maps / result chains?
The main parts of road maps
Creating road maps
Group exercises
Using road maps
Making the Plan
Road Maps
Overview presentation

## Slide 20
Making the Plan
Road Maps
How to construct a road map?
STRATEGY
ACTIVITY
(and tasks)
DESTINATION
(result)
DESTINATION
(outcome)
TARGET
if we do this…
we should reach this…
SIGNPOST
(indicator)
finally reach this…
then we do this…
SIGNPOST
(indicator)
we can check these…
which helps these
how are we
going to travel
CHECK
CHECK
CHECK
by this time…
by this time…
by this time…
ACTIVITY
(and tasks)
SIGNPOST
(indicator)
Notes: This diagram is another way of talking about how result chains fit together
Starting at the Strategy
If we do the ACTIVITY
We should see the DESTINATION
Which will be indicated by the SIGNPOST
Then we can move to the next ACTIVITY and so on

## Slide 21
Step 1. Select a target and threat you want to work on
Step 2. Set a Goal that your team believes will successfully address that threat or improve the target
Step 3. Select a high priority strategy that is designed to achieve that goal
Making the Plan
Road Maps
How to construct a road map
Notes: To make a result chain / roadmap, follow these steps
Take your time and think about each step
These can be done very informally as a conversation, recording the answers rather than using a diagram
But a diagram is a good visual tool and people seem to like them

## Slide 22
Step 4. Look at your situation analysis and identify the main things that cause the direct threat that must be changed
Factors might include:
  market forces
  social issues
  people’s level of knowledge of appropriate practices
  Politics
  Policies
  Enforcement issues
  In the case of invasive species – means by which they spread
Making the Plan
Road Maps
How to construct a road map?
Notes: Sometimes you need to do this step to remind you of the things you are trying to change
This step is not as important if you are doing the roadmaps with the same group you did the situation analysis and soon after doing that work

## Slide 23
Step 5. Working from the strategy to the goal, or the goal back to the strategy
Ask what the immediate results or outcomes of the strategy / actions should be?
What are the next outcomes you expect these
actions to produce?
What additional outcomes are necessary to
reduce your threat?
If you get stuck, ask “what would you do next?” and “if you do that activity well, what will be the result?”
Making the Plan
Road Maps
How to construct a road map?
Notes: Follow the steps suggested above.

## Slide 24
Left to Right or Right to Left?
Right to Left may be better for a new strategy – to ensure that the goals are met
Left to Right may better for a familiar strategy where the focus is on how it will get done
Either way can work – you decide
Making the Plan
Road Maps
How to construct a road map?
Notes: Another way is to work from right to left, asking what needs to happen to reduce the threat, what outcomes are needed to make that happen, etc.
Yet another way is to brainstorm intermediate results and then organize them along the chain, assuring that there are clear “if…then” linkages between each pair of results.

## Slide 25
Results oriented: Boxes contain desired results (e.g., reduction of hunting), and not activities (e.g., conduct a study).
Connected in a “causal” manner: There are clear connections of “if…then” statements between each pair of boxes.
Demonstrate changes: Each box describes how you hope the relevant factor will change (e.g. increase or decrease).
Making the Plan
Road Maps
Good Road Maps / Results Chains are…
Notes: Analysis of hundreds of results chains has identified a few characteristics of good results chains that include:
ONE - They are Results oriented: Boxes contain desired results (e.g., reduction of hunting), and not activities (e.g., conduct a study).
TWO – They are Connected in a “causal” manner: There are clear connections of “if…then” statements between each pair of successive boxes.
THREE – They Demonstrate changes: Each box describes how you hope the relevant factor will change (e.g., improve, increase, or decrease).

## Slide 26
Relatively complete: There are sufficient boxes to construct logical connections but not so many that the chain becomes overly complex.
Simple: There is only one result per box.
Making the Plan
Road Maps
Good Road Maps / Results Chains are…
Notes: FOURTH – They are relatively complete – Teams do tend to make these overly complex – and it requires some skill to prevent large spaghetti chains.
FINALLY – like all good models – they are best when simple. They focus on the bare essentials – only one result per box - and should be limited to what you can reasonably influence. For example…not the occurrence of sun spots…

## Slide 27
Making the plan
Road Maps
Example Road Map - River

## Slide 28
Making the plan
Road Maps
Example Road Map - TEK

## Slide 29
What are road maps / result chains?
The main parts of road maps
Creating road maps
Group exercises
Using road maps
Making the Plan
Road Maps
Overview presentation

## Slide 30
Roadmaps focus on
achieving a result
not
doing activities
Making the Plan
Road Maps
Not a road map / results chain
Media
Campaign
Campaign
reaches
target
audience
Demand
for
caviar
drops
Price
for
caviar
drops
Sturgeon
not
over-fished
Healthy
Sturgeon
population
Healthy
Sturgeon
population
Notes: In comparison, what is NOT a results chain? It is not an implementation flow diagram.
An implementation flow diagram might look like this:
I'm going to implement a media campaign.
First, I'm going to implement a media campaign.
So, first I’m going to identify my target audience, then I'm going to produce educational materials, then I'm going to distribute educational materials.
This is a series of activities. If you try to read this chain in an if=then manner, you will see there are not causal linkages between the boxes. For example, if I identify my target audience, then I will produce educational materials? No, this is not a direct causal result of identifying my target audience.
Reading your chain as a series of if-then relationships is a good way to make sure that components of your results chain are not an implementation chain. This is a very common mistake.

## Slide 31
Making the Plan
Road Maps
Which of the Following is NOT a Road Map?
Notes: Now, it’s your turn to determine which of these three chains does not meet the criteria for good results chains. Please look at these chains and then select one of the following responses. Be sure to click the “submit” button to see if your response is correct. To advance to the next slide you will then need to click the “continue” button. If needed, you can go back to previous slides to review the criteria.
Chain A is not a results chain. It mixes implementation steps with results. For the most part, it shows a series of activities the team will do. These activities, or implementation steps, include: identify key decision makers, educate decision makers, and research and develop regulations. The chain does include a few boxes that are more results-oriented. These include: decision makers pass laws, no wildlife trade, and jaguar populations increased.

## Slide 32
Making the Plan
Road Maps
Your Turn: Add the Missing Result
Notes: Now it’s your turn again. Look at the following results chain and think about what result is missing in the box marked by a question mark. Type your response in the box and click submit when you are done to see if your answer is correct.

## Slide 33
Making the Plan
Road Maps
Your Turn: Add the Missing Result
Notes: The correct answer is:
Loggers use certified harvesting methods
Did you have a similar response? If not, make sure that your result follows an if-then relationship with the results on either side

## Slide 34
Making the Plan
Road Maps
Your Turn: Create a Road Map
Using the Following Results
Citizens eradicate invasive plants
Healthy native wetland vegetation
Citizens have skills to eradicate invasive plants
Train citizens to eradicate invasive plants
Citizens knowledgeable of local invasive plants
Invasive plants decreased

## Slide 35
Making the Plan
Road Maps
Your Turn: Create a Road Map
Using the Following Results
Notes: The correct answer is that “invasive plants decreased” should go in the purple box, because it describes the threat you will reduce, and “Healthy native wetland vegetation” should go in the oval, as your conservation target.
Your complete results chain would look like this.
You may want to take a moment to read the results chain from left to right and make sure that it meets all of the criteria – that all the boxes are results, not implementation steps, they are simple (one result per box), and the if-then causal logic holds well.

## Slide 36
Projects need Road maps
Making the Plan
Results chains
Examples from a workshop
Notes: When you do these in a workshop using paper and sticky notes, you will end up with something that looks like this with a mix of activities and results.

## Slide 37
What are road maps / result chains?
The main parts of road maps
Creating road maps
Group exercises
Using road maps
Making the Plan
Road Maps
Overview presentation

## Slide 38
Making the Plan
Road Maps
How we use a roadmap
STRATEGY
ACTION
DESTINATION
SIGNPOST
CHECK
WHAT is in the PLAN | WHAT do we DO | WHAT do we CHECK / LEARN
Workplan – jobs, who will do them, resources | Day-to-day on-ground and other work | Is work being done? Are there issues, changes?
Objectives - what changes if we do the jobs | Team leaders / managers use this to guide work | Is destination is getting closer? Are we on the right path?
Goals – what happens to our values if we do the jobs | Team leaders / managers use this to guide work | Are the values are getting better / worse? Why?
Indicators – what will we measure, who, how, resources | Monitoring activities – eg surveys, mapping – capture and store | What does the evidence tell us?
Monitoring Plan – who, when, how will we review | ‘Toolbox’ meetings / workplan meetings | When do we do check each of these?
VALUES
Notes: This slide shows how the different parts of the roadmap are connected to:
What is in your plan
What you do
And what you will review / check later in the monitoring.

## Slide 39
Making the Plan
Results chains
A final example
Notes: This is an advertisement that shows an idea of what a result chain is in a silly situation – people like it

## Slide 40
Making the Plan
Road Maps
Additional Resources

## Slide 41
Making the Plan
Road Map
Workshop Exercise
Creating a roadmap
Give yourself plenty of room
‘Bookend’ your roadmap – on the Left put your Strategy, on the Right your Target and Threat (if there is one)
Brainstorm some activities and put them in date order
Then talk through the ‘results’ the activities will create
Make sure the results can be connected through “if-then” statements e.g. IF I get this result, THEN I can get the next result – read them out loud
Keep doing this until there is a clear link between your Strategy and the Threat / Target

## Slide 42: Attribution
Product of the Conservation Coaches Network, 2019
These presentations were adopted of materials from members of the Conservation Coaches Network.
CCNet strongly recommends that this presentation is given by experts familiar with the adaptive management process presented by the Conservation Measures Partnership’s Open Standards for the Practice of Conservation / Community of Practice – Indigenous CS projects and CS projects on Indigenous Land and Waters.
You are free to share this presentation and adapt it for your use. Please attribute the work to CCNet. If you significantly alter, transform, or build upon this work, it may be appropriate to remove the HCP logo.