## 1-Year Option
# | Task | Complete | Who | Deadline | Cost | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
KEY
Major Deadlines
Tasks
Phases
Holidays

## 3-Month Option
[6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
# | Task | Complete | Who | Deadline | Cost
KEY
Major Deadlines
Tasks
Phases
Holidays

## Sample 1-Year Option
NOTE: THIS IS A HYPOTHETICAL WORKPLAN; ONLY THE ACTIONS AND TASKS ARE ACTUALS. FOR THE FULL LIST OF ACTIONS AND TASKS, SEE THE BERING SEA STRATEGIC PLAN.
Activity/Task # | Work breakdown for Commercial Fisheries Objective 3a: Reduce the number of albatross and other seabirds caught in longlines & nets by 90% by 2010 in US waters and by 50% by 2015 in Russian waters. | Complete | Who | Deadline | Cost | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
3a.1 | Expand tori line use in Russian longline fleet
3a.1.1 | Expand education program with fishermen |  | K. Alvarez (WWF) | 2002-11-27 | 1000
3a.1.2 | Secure funding for tori lines and other equipment; purchase and ship. |  | J. Miller (TNC) | 2003-01-10 | 2000
3a.1.3 | Tori lines distribution between main Russian longline fishing companies |  | L. Ko (EPA) | 2003-01-10 | 2000
3a.1.4 | Other mitigating equipment promotion (integrated weight line, etc.) |  | K. Alvarez (WWF) | 329847 | 3000
3a.2 | Improve understanding of interactions between US fisheries and incidental seabird take
3a.2.1 | Better quantify seabird/gear interaction rate in trawl fisheries (Lead = USFWS) |  | K. Alvarez (WWF) | 2003-01-10 | 1000
3a.2.2 | Coordinate development of database of spatial and temporal distribution of all fishing effort in the Bering Sea Ecoregion. |  | J. Miller (TNC) | 2003-01-15 | 2000
3a.2.3 | Quantify drop-off rate for seabirds caught on longlines (those that go under and don’t come up) (Lead = USFWS) |  | L. Ko (EPA) | 2003-03-09 | 2000
3a.3 | Obtain ban on high seas driftnet fisheries in Russia
3a.3.1 | Conduct an analysis of current high-seas driftnet practices |  | K. Alvarez (WWF) | 2003-02-11 | 1000
3a.3.2 | Lobby Russian government |  | J. Miller (TNC) | 2003-02-19 | 2000
3a.3.3 | Lobby Japanese government with assistance of the WWF Japan |  | L. Ko (EPA) | 2003-04-30 | 2000
3a.4 | Establish Observer Program in Russia
3a.4.1 | Develop and implement program |  | J. Miller (TNC) | 2003-04-18 | 1000
3a.4.2 | Propose changes for Russian legislation, regulations & system of observers activities |  | L. Ko (EPA) | 2003-04-30 | 2000
KEY
Major Deadlines
Tasks
Phases
Holidays

## Sample 3-Month Option
NOTE: THIS IS A HYPOTHETICAL WORKPLAN; ONLY THE ACTIONS AND TASKS ARE ACTUALS. FOR THE FULL LIST OF ACTIONS AND TASKS, SEE THE BERING SEA STRATEGIC PLAN.
[6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Activity/Task # | Work breakdown for Commercial Fisheries Objective 3a: Reduce the number of albatross and other seabirds caught in longlines & nets by 90% by 2010 in US waters and by 50% by 2015 in Russian waters. | Complete | Who | Deadline | Cost | 11/25 - 11/29 | 12/2 - 12/6 | 12/9 - 12/13 | 12/16 - 12/20 | 12/23 - 12/27 | 12/30 - 1/3
3a.1 | Expand tori line use in Russian longline fleet
3a.1.1 | Expand education program with fishermen |  | K. Alvarez (WWF) | 2002-11-27 | 1000
3a.1.2 | Secure funding for tori lines and other equipment; purchase and ship. |  | J. Miller (TNC) | 2002-12-10 | 2000
3a.1.3 | Tori lines distribution between main Russian longline fishing companies |  | L. Ko (EPA) | 2002-12-10 | 2000
3a.1.4 | Other mitigating equipment promotion (integrated weight line, etc.) |  | K. Alvarez (WWF) | 2002-12-20 | 3000
3a.2 | Improve understanding of interactions between US fisheries and incidental seabird take
3a.2.1 | Better quantify seabird/gear interaction rate in trawl fisheries (Lead = USFWS) |  | K. Alvarez (WWF) | 2002-12-06 | 1000
3a.2.2 | Coordinate development of database of spatial and temporal distribution of all fishing effort in the Bering Sea Ecoregion. |  | J. Miller (TNC) | 2002-12-11 | 2000
3a.2.3 | Quantify drop-off rate for seabirds caught on longlines (those that go under and don’t come up) (Lead = USFWS) |  | L. Ko (EPA) | 2002-12-09 | 2000
3a.3 | Obtain ban on high seas driftnet fisheries in Russia
3a.3.1 | Conduct an analysis of current high-seas driftnet practices |  | K. Alvarez (WWF) | 2002-12-17 | 1000
3a.3.2 | Lobby Russian government |  | J. Miller (TNC) | 2002-12-18 | 2000
3a.3.3 | Lobby Japanese government with assistance of the WWF Japan |  | L. Ko (EPA) | 2002-12-26 | 2000
3a.4 | Establish Observer Program in Russia
3a.4.1 | Develop and implement program |  | J. Miller (TNC) | 2003-01-06 | 1000
3a.4.2 | Propose changes for Russian legislation, regulations & system of observers activities |  | L. Ko (EPA) | 2003-01-06 | 2000
KEY
Major Deadlines
Tasks
Phases
Holidays