## Cover Page
Conservation Audit
Guidelines & Tool
Version 2.0, July 2018
What are these guidelines and tool for? | Assessing conservation programs against industry standard best design and adaptive management practices.
Who are they for? | Anyone involved in a conservation effort, including program managers, senior management, evaluators, strategic planners, coaches, and funders.
When do you use them? | At any time in the program cycle.
Who and how is it done? | You can do it, a team can do it, peers can do it and hired external agents can do it! As a desk study, face-to-face exercise, virtually or as a combination of approaches.
Can I adapt these to my program's or organization's specific terminology or needs? | This CMP product has been developed and shared as an 'Open Source' product under a Creative Commons License (see below). This material can thus be shared, repurposed, remixed and modified as needed, provided that you provide attribution to CMP as the source product and release any derivative products with a similar open source licence. The tool and guidelines have been locked to protect formatting and formulas. See the Instructions tab for guidance on unlocking and editing this workbook.
How do I cite these guidelines and tool? | This work is licensed under a Creative Commons Attribution-ShareAlike 4.0 International License. Please cite this document as: O'Neill, E. and S.O'Connor. 2018. Conservation Audit Guidelines and Tool, v. 2.0. Conservation Measures Partnership. | Click here to see CC License
For CMP, Authored by:
Elizabeth O'Neill | Sheila O'Connor
Managing Director, EON Impact Consulting, LLC | Independent Consultant
Colorado, USA | Devon, UK
Current CMP Member Organizations:
African Wildlife Foundation (AWF) | National Fish and Wildlife Foundation (NFWF)
Bush Heritage Australia | Nature Conservancy of Canada (NCC)
Conservation International (CI) | NatureServe
Disney’s Animals, Science, and Environment | Rare
Foundations of Success (FOS) | The Nature Conservancy (TNC)
The Gordon and Betty Moore Foundation | US Agency for International Development (USAID)
International Crane Foundation (ICF) | US Fish and Wildlife Service (USFWS)
International Fund for Animal Welfare (IFAW) | Walton Family Foundation
Jane Goodall Institute (JGI) | Wildlife Conservation Network (WCN)
Keith Campbell Foundation for the Environment | Wildlife Conservation Society (WCS)
The Leona M. and Harry B. Helmsley Charitable Trust | WildTeam
Margaret A. Cargill Foundation | WWF
For information regarding this protocol – or to provide comments on it – contact
The Conservation Measures Partnership at audits@ConservationMeasures.org
Conservation
Measures
Partnership
CMP

## Introduction
INTRODUCTION
CONSERVATION AUDITS: ASSESSING ALIGNMENT OF PROGRAMS WITH INDUSTRY-STANDARD BEST DESIGN AND MANAGEMENT PRACTICES
Background
Working from the hypothesis that meeting best practice "standards" for conservation program design, management and learning leads to greater efficiency and conservation impact, in 2002, the Conservation Measures Partnership (CMP) developed and promoted the adoption of the Open Standards for the Practice of Conservation (Open Standards or OS) (figure at right; the most updated version is from 2013). To complement the Open Standards and to assess the extent to which they—or compatible organization-specific design and management best practice or standards—were being followed, CMP member organizations also developed the practice of conservation auditing (see history, Box 1). Conservation auditing, which also could be known as "best practice assessment" is defined as a review of the process and practice of conservation rather than the results achieved. More specifically, a conservation audit is a review of the extent to which the design and management of a conservation program reflect accepted industry-standard best practices.
Although the practice of conservation auditing declined after 2007, CMP continued to advance the adoption of the best practices outlined in the OS, and according to a 2015 evaluation of CMP and its sister organization, the Conservation Coaches Network (CCNet), “In one form or another, fully or partially, the Open Standards are now used by the world’s two largest implementing conservation NGOs (WWF and TNC) and by a dozen other small and medium-sized conservation organizations. The Open Standards have reached thousands of practitioners and been used on tens of thousands of projects around the world” (Redford et al. 2015). Recognition also has grown of the need to ensure that conservation programs are guided by robust theories of change supported by pragmatic and informative monitoring and evaluation systems. Thus it seems that the time is right for CMP to revive the practice of conservation auditing.
The primary goal of conservation audits is to increase the likelihood of positive outcomes through an assessment of the design and execution of conservation programs as they adhere to the OS or other similar approaches. Regular and structured conservation audits increase the rigor and effectiveness of conservation programs by increasing use of accepted sound practice and, in so doing, reinforcing the credibility of stated results. On an individual basis, a conservation audit promotes excellence in conservation program management, and emphasizing and improving the adaptive quality of the work proposed and undertaken. Some specific objectives developed for past conservation audits are listed in Box 2.
Conservation audits can be performed on programs of any scale, from individual projects to local, site-based conservation efforts to region-wide geographic programs to programs focused on a particular theme of work (e.g., illegal wildlife trade, global markets, climate change). The use of audits at an organizational level is discussed briefly later in the guidance. Conservation audits can be conducted by program teams themselves (with a facilitator or not), by peer teams, or by externally contracted consultants.
About This Document
This document provides a tool, framework and guidelines for conservation auditing, or best practice assessment. To use this document, we suggest that you read through the instructions on the following worksheet before proceeding to the tool (darker green tabs). You also may want to review the supporting guidance found on the orange tabs in order to understand what a conservation audit is and isn't, whether an audit is what you need, and what type of approach you might employ to meet your auditing needs. These sections should take no more than 30 minutes to read and process. Additional information is found in a series of Appendices (tabs colored blue). We note that for the purpose of this guidance, the term "program" is used to be all-encompassing of conservation projects or programs (which typically are comprised of multiple projects). This guidance document is appropriate for use at any scale, from small, localized, short-term projects to large, complex, and long-term programs. Guidance is also provided on using this guidance to support organizational-scale auditing. As with the array of tools and guidance made available by CMP, these are open source guidelines to be used by anyone wishing to assess and strengthen the quality of design and management of a conservation program. It also is CMP's hope that users will provide feedback on ways to improve this guidance, which would be incorporated into future versions. Please send any input for CMP to audits@conservationmeasures.org.
Box 1. A bit of history From 2003-2006, CMP member organizations conducted more than 40 conservation audits. During this time, CMP also had a targeted initiative to develop conservation audit guidelines and promote the practice overall. Although the benefits of conservation auditing were found to outweigh the costs, the practice as it was originally conceived by CMP largely fell into disuse (O’Neill 2007, Redford et al. 2015). While CMP did not investigate why this was the case, a few reasons are outlined here: 1) at the time conservation auditing was initiated, the OS had not yet had broad uptake, thus auditing against them may have been premature, 2) conservation organizations and funders historically did not place adequate attention on systematic planning and adaptive management, and so a system for auditing against the quality of these practices was similarly not a high priority, and 3) there has been a tendency to emphasize external independent evaluation over the auditing of design and management process, as there is a stronger desire to understand the extent to which the planned results of a program have been achieved and why or why not. In some cases, however, the basics of conservation auditing have been incorporated into evaluation frameworks and exercises (O’Neill et al. 2012)
Box 2. Some specific objectives of past conservation audits
> To promote program improvement through a “quality assurance review” and discussion of the organizational best practices for strong project management.
> To increase the likelihood of positive outcomes and the credibility of self-reported results.
> To generate credibility around the work the program is doing and the impacts it is having.
> To support learning: program team learns from the conservation audit team, peer-reviewers learn from the program, and wider organization learns through sharing of audit findings.
> To build confidence among senior management and donors that their investments are worthwhile.
> To help the project team to raise 'the quality' of the conservation process by identifying and adopting best practices, and by so doing, increase the likelihood of biodiversity being conserved.
> To look at how the program makes decisions, develops and implements its work, and how it shares the results of its work in order to improve conservation outcomes and sustainability.
> To determine adherence to the organization's global program philosophy and priorities, stated policies and procedures, and recommended methods of intervention.
> To pilot test the audit process itself.

## Instructions
AUDIT TOOL INSTRUCTIONS
Steps
Using the audit tool is very straightforward and involves the following steps:
1. | Decide WHETHER TO AUDIT, based upon considerations of potential benefits, what an audit can provide, and whether the program in question is in need of a conservation audit. If needed, decision support can be found via the link at right. | Click here to jump to the Whether to Audit worksheet.
2. | Decide WHAT TYPE OF AUDIT APPROACH you will employ, deciding among self-audit, facilitated self-audit, peer-led audit, externally-contracted audit, or an audit within an evaluation. This is a particularly important decision that can affect the quality of your audit process and outcome, and so we recommend reviewing the decision support found via the link at right. | Click here to jump to the Type of Audit worksheet.
3. | Initiate your AUDIT PROCESS, doing necessary preparatory work before proceeding to the steps below. For reference, the general steps to follow during an audit process can be found via the link at right. | Click here to jump to the Audit Process worksheet.
4. | Complete the AUDIT SUBJECT worksheet to capture basic information on the program being audited, who is conducting the audit, who was consulted to inform the audit, and documentation and data utilized. | Click here to jump to the Audit Subject worksheet.
5. | Complete the AUDIT TOOL worksheet by using best available information (documentation, data, interviews, survey, self assessment) to assign a rating for each audit criterion, choosing from the annotated scale that ranges from 1 to 4. Using the dropdown menu, capture your ratings in column F. In Column G, provide a brief written justification for your rating. | Click here to jump to the Audit Tool worksheet.
6. | Review the automatically generated REPORT and prepare a MANAGEMENT RESPONSE. Summary ratings for each audited best practice/step will be captured in the REPORT worksheet. The auditor, audit team, or audit facilitator should review the specific criterion ratings (captured in the AUDIT TOOL) as well as the summary ratings with the audited program team and then pass the workbook on to the team so they can then complete the management response columns of the REPORT worksheet. | Click here to jump to the Report and Management Response worksheet.
7. | Write up a REPORT. If needed/desired, the auditors should compile a report to document the exercise. Beyond including the AUDIT SUBJECT worksheet, the AUDIT TOOL worksheet, and the REPORT worksheet (including the completed management response), it is recommended that auditors attach a narrative summary summarizing the audit findings, priorities for program improvement, and next steps.
Notes and Tips
The following notes and tips may help with conducting a smooth conservation audit exercise:
1. | Avoid being overly concerned with precise terminology. While this tool was designed following the terminology utilized in the Open Standards, the program being audited may have been designed/managed according to an organization specific or other adaptive management framework that aligns to the OS, but uses different terms. In the end, as long as the intent or definition is the same, terms can be used interchangeably.
2. | Focus on the spirit of the law versus the letter of the law. The audit tool provides detailed criteria for rating each design/management sub-step. These were developed to be clear and pragmatic and not overly dogmatic. Rather than focusing overmuch on what exactly is said in the Open Standards, it is recommended to rate based upon the criteria provided.
3. | Adapt to organization-specific frameworks or needs, but only as necessary. Various CMP member organizations and others have developed their own internal design and management standards, some cognizant of the Open Standards and others not. Where there is significant divergence between an organizational framework and the OS, auditors may first need to adapt the audit tool to align with organizational best practice guidelines. At this time, most of the content of this workbook is locked. To unlock it, the password is ConsAudits. It is recommended that only someone proficient in Excel edit the workbook to ensure that links between sheets are maintained and that formulae continue to reference the correct ranges of cells.
4. | If necessary, auditors may focus on specific aspects of the audit tool. In some cases, a more rapid or cursory audit process may be desired. In these cases, auditors can work with the program under review (or with organizational leadership or other "clients" requesting the audit) to select priorities within the audit framework. For example, it may be possible to skip the operational aspects (Step 2C) if the desired focus is principally on the conservation program strategy design and execution.
5. | Consult the glossary and criteria for key terms in the appendices. Where concepts or terms are not familiar, the Glossary and/or Criteria for Key Terms in the appendices may prove helpful.
6. | Consult the full text of the Open Standards where needed. The audit tool numbers the various steps and sub-steps in accordance with the numbering found in the Open Standards. The Open Standards also are translated in multiple languages. | http://cmp-openstandards.org/download-os/
7. | The audit tool can be used for thematic (i.e., non-place-based) programs with some modifications. Keep in mind that the OS is “Open” to allow for adaptations of processes and practices so that they are useful in different settings and for various types and scales of programs. | Click here to jump to guidance on auditing thematic programs.
8. | This audit tool can be used to inform organizational scale audits. When considering the use of the audit tool at the organizational level, consider carefully what your objectives are. | Click here to jump to guidance on using this tool for org audits.
9. | To make the tool and report easier to share, you can HIDE all the other tabs by clicking on format, then sheet, then hide.

## AUDIT SUBJECT
AUDIT BASIC INFORMATION | RESPONSE |  | COMMENTS
Date(s) over which audit conducted
Organization
Program (or Project) Name
Location
Annual Operating Budget of the Program
Approximate Human Resources # FTE
Approximate Duration of the Program
Key Goals/Objectives
Title and Year of the Program's Latest Strategic Plan
Name(s) and Title(s) of Person(s) Leading the Program
Title and Date of the last Program Evaluation Report
Format of Audit (see drop down list)
General Description of Approach to Audit (e.g., desk review based on documentation only, desk review of documentation plus interviews, field visits, surveys, team consultations, etc.)
What is the design and management standard/framework primarily utilized by the program (e.g., none, Open Standards, or an organizational framework)?
What are other relevant organizational policies the program should be following regarding design and implementation of strategy (e.g., gender policy, indigenous peoples policy, operations guidelines, etc.)?
What are relevant organizational systems that the program should be using to capture monitoring data (if any)?
Audit Team/Participants
Audit Leader or Facilitator Name | Title | Organization | Email
Additional People Conducting the Audit | Title | Organization | Email
Audit Informants (i.e., people consulted, beyond the audit team) -- add rows as needed
Name | Title | Organization | Brief Description of Relation to the Audited Program
Literature Reviewed (list citations below) -- add rows as needed

## AUDIT TOOL
CONSERVATION AUDIT OF: | 0 |  | DATE: | 0
(cells at right auto-fill) | 0
Open Standards V3.0 Steps and Audit Criteria | 4: No or minimal improvement needed | 3: Some improvement needed | 2: Significant improvement needed | 1: Does not exist/ not developed. | Assign Rating (1-4) | Brief Justification for Rating / Comment
1. CONCEPTUALIZE
1A. Planning Purpose & Program Team
A strategic plan/framework guides the focus and efforts of the program. | There is a recently developed (i.e., <3-5 years) strategic plan/framework that is actively being used to guide the focus and efforts of the program. | There is a recently developed (i.e., <3-5 years) strategic plan/framework that some staff are using as a guide to focus the efforts of the program. | There is a strategic plan/framework but it is not particularly recent and/or it does not appear to be used regularly by program staff. | There is no strategic plan/framework for the program. | 4
Who designed and who is implementing the plan is clear, and necessary roles known, understood and without gaps. | Who designed and who is intended to lead implementation of the plan is clear and known to all relevant staff and stakeholders. All roles are understood and there are no gaps. | Who designed and who is intended to lead implementation of the plan is somewhat clear to at least some staff and stakeholders. Roles are somewhat understood, and there may be some gaps. | Who designed and who is intended to lead implementation of the plan is known to a few select staff. Roles are not entirely clear and the team is not yet complete. | Who designed and who is intended to lead implementation of the plan is not clear. Roles are not clear or understood. | 2
1B. Scope, Vision & Conservation Targets
Program scope defined (i.e., what defines the boundaries of the work and/or what the program seeks to influence, place-based or thematic). | Scope has been documented and shared in plans and supported where necessary with maps, issues papers etc. as appropriate. Relevance of the scope to the organization and externally is clear. | Evidence that scope has been generally defined and shared, with simple supporting documentation. Relevance of the scope is mostly clear. | Scope not yet defined but activities have been put in place to decide scope i.e. workshops etc. | Scope not defined nor considered. | 3
If program is place-based, there is a map of program scope. | Maps clearly portray the geographic focus of the program at a sufficiently fine resolution to show key features (e.g., boundaries, surrounding communities and/or extractive activities/ concessions, geographic elements, etc.). | The geographic focus of the program is mapped at a sufficiently fine resolution but key features are not shown. | The geographic location of the program is identified on a map but at a low resolution and/or the program boundaries are unclear. | There is no map showing the geographic focus of the program. | 4
There is a relatively general, aspirational, and brief vision statement that summarizes the desired state or ultimate condition of the program scope and aligns with the organization’s or partnership’s overall mission. | A relatively general, aspirational, and brief vision statement summarizes the desired state or ultimate condition of the program scope. The vision aligns to the organization's mission and is agreed by program leaders, involved partners, and key stakeholders. | The vision is general, relatively brief, visionary, audience appropriate, and aligns to organization's mission. It has not been shared, but there is a strategy for reaching a shared vision. | Vision does not relate to the program scope and/or organization's mission or is inappropriate for audience (or there is no strategy for achieving a shared vision). | There is no vision statement. | 1
A limited number of conservation targets (e.g., species, habitats, ecological processes, and nested targets where appropriate) defined and justified. | A clear and specific list of the species and habitats that are the focal conservation targets is documented and clearly justified in relation to the scope. Or for thematic projects, the project has clearly identified the strategic issues (e.g. environmental or ecological footprint)/ threat to be addressed and has explained how this relates to biodiversity. | There is a list of conservation targets or strategic issues (e.g. environmental or ecological footprint) and/ or a dedicated section on these in the plan or project documents. However there is limited justification provided. | There is no list and/or dedicated section of a document regarding conservation targets or strategic issues (e.g. environmental or ecological footprint). However targets are discernible in documentation and/ or can be identified from direct discussion with project staff. | No conservation targets are discernible and project staff are unaware or unable to describe them. | 2
If relevant, human well being targets selected and justified. | If relevant, a clear and specific set of human well being targets are documented and clearly justified in relation to the scope and situation and stakeholder assessments. | There is a list of human well being targets, however there is limited justification provided. | There is no list of human well being targets, however targets are discernible in documentation and/ or can be identified from direct discussion with staff. | No human well being targets are discernible and staff are unaware or unable to describe them. | 3
Relevant organizational policies considered and incorporated. | Relevant organizational policies (e.g., gender, indigenous peoples) have been considered and implications for the the strategic approach identified. | Relevant organizational policies (e.g., gender, indigenous peoples) have been somewhat considered and implications for the strategic approach identified. | Consideration of relevant organizational policies has been limited; key implications have not been identified to incorporate within the strategic plan. | Relevant organizational policies have not been considered or incorporated. | 4
1C. Critical Threats
Threats identified, rated, and ranked to assign priority and to prioritize factors that affect the scope. | Threats directly driving decline in the condition of conservation targets and that affect the scope are defined, rated, and ranked, with justifications clearly articulated and supported with documentation and data. | Threats directly driving decline in the condition of conservation targets and that affect the scope are defined, rated, and ranked, but justifications are not well articulated and/or supporting documentation and data are lacking. | Threats directly driving decline in the condition of conservation targets and that affect the scope are defined but not rated or ranked. | Threats directly driving decline in the condition of conservation targets and that affect the scope are not defined. | 1
1D. Conservation Situation
Indirect threats and opportunities identified and analysed. | Based upon thorough assessments, there is a clear and comprehensive understanding of context affecting the scope and targets, including drivers of threats, opportunities and their interlinkages. Priorities to be addressed are clear and justified. | There is evidence of discussion of context but this evidence indicates that the complexity of the context is not fully comprehended. However this has been recognised and further work is scheduled to undertake greater analysis before priorities for focus and action are set. | Analysis of context is basic and general, with relationships among factors not understood in detail. Priorities for focus and action are not very clearly defined or justified. | There is little or no evidence or understanding of the context. | 2
Stakeholders and other influential actors and their primary interests identified and assessed. | Based upon thorough assessments, there is a clear and comprehensive understanding of the stakeholders affecting or affected by the context (above). Key stakeholders have a shared understanding of this context, and are engaged in program design where possible. | There is evidence of discussion of stakeholders but this evidence indicates that the complexity of the relationships/needs/roles of the stakeholders is not fully comprehended. However this has been recognised and further work is scheduled to undertake greater analysis before priorities for focus and action are set. | Analysis of stakeholders is very basic and general. Priorities for focus and action are not clearly defined or justified. | There is little or no evidence or understanding of the stakeholders involved. | 3
Conceptual model illustrates key cause/effect relationships among targets, threats, and key factors (i.e., drivers, indirect threats). | There is a detailed graphic representation or comprehensive text discussion of the interrelationships among targets, threats, and underlying key factors. | There is a general graphic representation or discussion of the interrelationships among targets, threats, and underlying key factors. | There is a no graphic representation of the interrelationships among targets, threats, and underlying key factors, but there is a basic discussion of these in documentation. | There is no conceptual model or discussion of interrelationships. | 4
2. PLAN ACTIONS & MONITORING
2A. Formal Action Plan: Goals, Strategies, Assumptions, Objectives
Goals articulated describing desired future state of conservation and human well being targets in SMART terms (i.e., Specific, Measurable, Attainable, Relevant, Time-bound) | Goal statements of what success looks like are described for each focal target and their desired future condition. Goals are SMART (specific, measurable, ambitious yet attainable, relevant, time-bound). | Goal statements of what success looks like are described for each focal target and their desired future condition but don't meet all of the SMART criteria. | There are goal statements but they are poorly articulated. | There is no single document or framework used by all project staff which sets out the goals. | 1
Objectives articulated that describe the desired future state of highest priority threats and opportunities in SMART terms. | Objectives clearly describe the desired future state of highest priority threats and opportunities in SMART terms, and for a 3-5-year timeframe. | Objectives clearly describe the desired future state of highest priority threats and opportunities but are not fully "SMART." | There are objective statements regarding priority threats/ opportunities but they are not well articulated or fully SMART. | There are no objective statements regarding priority threats/ opportunities. | 2
Optimal strategies identified, described and linked to threats and opportunities (or other factors) in the situation/conceptual model that they seek to affect. | Optimal strategies are clearly defined/described. Strategies and tactics have been selected based upon systematic considerations of feasibility, affordability, organizational niche, and likely impact on threats/ targets/ footprint, etc. | Optimal strategies are defined/ described but how they were selected is somewhat unclear and/or there are apparent issues regarding their feasibility, affordability, alignment with organizational niche, and/or likely impact on ultimate targets and key factors. | Optimal strategies are defined/ described but how they were selected is wholly unclear and/or it is apparent that criteria such as feasibility, affordability, alignment with organizational niche, and/or likely impact were not considered. | Optimal strategies are not defined. | 3
Theories of change (e.g., results chains for each strategy) show assumed causal relationships from strategies to attainment of programmatic goals. | The project has described the relationships among conservation targets, threats, opportunities, stakeholders, and strategies and has shown how it will create change through a tool such as a theory of change, logic model, results chains, Miradi model, and/or log frame. The tool is being used to ensure logic of strategic approach and clarity of communication to staff, partners and stakeholders. | A theory of change has been described and documentation shows evidence of the theory being tested through a logic tool (e.g. results chains). However this has not been optimally used to communicate the theory internally or to partners/ stakeholders etc. externally. | A theory of change has been described but it is relatively basic and documentation shows little evidence of the theory being tested through a logic tool. | There is no logic model or theory of change described. | 4
Objectives developed from the theory of change defined in SMART terms, describing critical results/outcomes to be attained. | Objectives are defined in SMART terms, describing critical results/ outcomes to be attained via the execution of each strategy. | Objectives are defined and describe critical results/ outcomes to be attained via the execution of each strategy, but not in SMART terms. | Objectives are defined, but not in SMART terms and/or only for certain but not all strategies. | Objectives are not defined. | 1
Goals, objectives, strategies, strategic objectives, and activities captured in a formal action plan. | Goals, objectives, strategies, strategic objectives, and activities captured in a formal action plan that is concise, clear, and shared by all relevant staff, partners, and stakeholders. | Goals, objectives, strategies, strategic objectives, and activities captured in a formal action plan but it is not necessarily concise or clear, and/or it is not shared by all relevant staff, partners, and stakeholders. | There is a general action plan that captures goals, objectives, strategies, strategic objectives, and activities but it is not concise, clear, or shared by all relevant staff, partners, and stakeholders. | There is no formal action plan. | 2
2B. Formal Monitoring Plan
Audiences and end-uses of monitoring data, and associated information needs, clearly defined. | Audiences and end-uses of monitoring data, and associated information needs, are clearly defined and known to relevant program staff. | Audiences and end-uses of monitoring data, and associated information needs, are clearly defined but are known only to M&E staff. | Audiences and end-uses of monitoring data, and associated information needs are only partially defined. | Audiences and end-uses of monitoring data, and associated information needs are not defined. | 3
Goal- and objective-level indicators and measurement methods defined (including impact, outcome and output indicators). | An appropriate, informative, feasible set of indicators and measurement methods (including data requirements and how data will be collected, managed/captured, analyzed, and utilized) defined for all or most of the goals and objectives. | Appropriate, informative, feasible set of indicators and measurement methods defined for more than half of the goals and objectives. | Indicators and measurement methods defined for less than half of the goals and objectives. | Indicators and measurement methods defined for few or none of the goals and objectives. | 4
Baselines for each indicator are known and supported by credible data. | Baselines are provided for all or most of the identified indicators. | Baselines are provided for more than half of the indicators. | Baselines are provided for less than half of the indicators. | Few or no baselines are provided. | 1
Monitoring plan captures audiences, information needs, indicators, methods, and baseline conditions as well as defining process of review of information. | Monitoring plan captures audiences, information needs, indicators, methods (including data requirements and how data will be collected, managed/captured, analyzed, and utilized), and baseline conditions. It is clear when and how the data is reviewed. | Monitoring plan and process of review exist but is missing one or two of the elements indicated at left under Score 4. | Monitoring plan and process of review exist but is missing many of the elements indicated at left under Score 4. | There is no monitoring plan. | 2
2C. Operational Plan
Funding needs and strategy developed. | Funding requirements to support the planned program are robustly defined and documented. A fundraising strategy exists. | Funding requirements to support the planned program are estimated and documented. A basic funding approach exists or can be articulated by staff. | Funding requirements to support the planned program only generally estimated. Funding strategy not developed. | Funding requirements to support the planned program not estimated. Funding strategy not developed. | 3
Human resource needs and strategy developed. | Human resources required to support the planned program are robustly defined and documented. An HR strategy exists. | Human resources required to support the planned program are generally described and documented. A basic HR approach exists or can be articulated by staff. | Human resource requirements to support the planned program only generally known HR strategy not developed. | HR requirements to support the planned program are not known. HR strategy not developed. | 4
Governance structure thoughtfully designed to respond to strategic plan. | The governance structure has been thoughtfully designed to respond to the strategic plan, and it is evident that "form is following function," in terms of staff structure. | The governance structure has been designed or adapted to respond at least partially to the strategic plan, and it generally appears that "form is following function," in terms of staff structure. | There is some evidence that governance structure has been designed to respond to the strategic plan but it does not appear that "form is following function," in terms of staff structure. | There is no evidence that governance structure has been designed to respond to the strategic plan. It does not appear that "form is following function," in terms of staff structure. | 1
Risk assessment conducted and mitigation plans formed. | There is a well researched risk analysis that provides a comprehensive assessment of overall risk level. Risks to achieving objectives and goals and have been identified. Monitoring tools and workplans includes risk mitigation and making timely adjustments. Risk of negative project impacts is addressed. | There is a risk analysis that provides good assessment of overall risk level. Risk mitigation measures are incorporated in action and monitoring plans. | Risk factors are somewhat defined but mitigation measures are unclear. | Risk factors have not been defined and are not being addressed. | 2
Life of the project estimated and an exit strategy formed. | Factors to support sustainability of results have been defined and actions taken to build these factors into strategies and workplans. The timeframe and desired condition of the sustainability factors (to support an effective and ethical exit) has been defined, and the factors are being monitored. | Factors to support sustainability of project results have been defined and actions taken to build these factors into strategies and workplans. An exit strategy is generally well defined. | An exit strategy has been discussed but requires more definition. And/or an exit strategy is defined but not fully documented or clearly linked to a consideration of the conditions necessary for sustainability. | Exit strategy is not defined or being addressed. | 3
3. IMPLEMENT ACTIONS & MONITORING
3A. Short-Term Work Plan & Timeline
Work plan details tasks, activities, timing, responsibilities to implement action, monitoring, and operational plans. | A work plan for an appropriate length of time (some organizations recommend 6 months - others two years) that details tasks, activities, timing, responsibilities to implement planned actions, monitoring, and operational plans. Relevant staff are familiar with and managing against the work plan. | A work plan for an appropriate length details tasks, activities, timing, responsibilities to implement planned actions, monitoring, and operational plans. At least some staff are familiar with and managing against the work plan. | There is a basic work plan describing tasks, activities, timing, responsibilities to implement planned actions, monitoring, and operational plans. At least one key staff is managing the program of work against the plan. | There is no work plan detailing tasks, activities, timing, responsibilities to implement planned actions, monitoring, and operational plans. | 4
3B. Program Budget
Program budget designed to generate desired results, and regularly tracked and updated. | A detailed budget identifies the financial resources required over the lifetime of the program necessary to implement all activities; budget includes necessary provisions for salaries, coordination, training, M&E, and reflection and learning costs. | Detailed budgets exist for the current implementation phase, consistent with the workplan and including M&E costs. The budget is adhered to and reviewed consistently. | Budgets exist but are basic or missing some key elements. Budget is reviewed and assessed periodically. | There are no workplans or budgets. | 1
Fundraising strategy implemented via multiple methods including proposals, memberships, adoptions, small gifts, etc. | A well developed and documented fundraising strategy using appropriate approaches exists. | A generally described fundraising strategy or set of agreed fundraising priorities is available. | A fundraising strategy is not fully described, proposals and other methods are somewhat ad hoc. | There is no fundraising strategy. Proposals or other methods are rarely developed/used. | 2
Required financial resources obtained to generate desired results. | The planned program of work is fully funded for the current operating year. The majority of required funding has been secured for at least the coming two years. | The planned program of work is more than 75% funded for the current operating year. At least half of required funding has been secured for the coming two years. | The planned program of work is more than 50% funded for the current operating year. At least 25% of required funding has been secured for the coming two years. | The planned program of work is less than 50% funded for the current operating year. Less than 25% of required funding has been secured for the coming two years. | 3
3C. Implement Plans
Strategies and actions being implemented as planned. | Strategies and actions are being implemented as planned. There is minimal work occurring that does not clearly align to the strategic plan. | Some aspects of planned strategies and actions are being implemented as planned, but there are important gaps. There is some work occurring that does not clearly align to the strategic plan. | Few aspects of planned strategies and actions are being implemented as planned. There are major gaps in implementation. There is significant work occurring that does not clearly align to the strategic plan. | Planned strategies and actions are largely not being implemented as planned. Much of the work that is occurring does not clearly align to the strategic plan. | 4
Monitoring plan being implemented as planned. | The monitoring plan is largely in implementation, including data collection, analysis, and data shared and accessible. | Some aspects of the monitoring plan are being implemented, but there are important gaps. | Few aspects of the monitoring plan are being implemented. There are major gaps in data collection and/or analysis. | The monitoring plan is largely not being implemented. | 1
Operations plan being implemented as planned (including funding and human resources strategies and intended governance structure and processes). | The operations plan is largely in implementation. | Some aspects of the operations plan are being implemented, but there are important gaps. | Few aspects of the operations plan are being implemented. | The operations plan is largely not being implemented. | 2
4. ANALYZE, USE, ADAPT
4A. Prepare Data for Analysis
Systems for capturing and maintaining program data developed and regularly used. | Robust systems for capturing and maintaining program monitoring data exist and are regularly used by all relevant staff. | There are good systems for capturing and maintaining program monitoring data though not regularly used by the team or all relevant staff. | There are basic systems for capturing and maintaining program monitoring data and these are used by one or more staff. | There are no systems for capturing and maintaining program monitoring data. | 3
4B. Analyze Results
Data or information used systematically to assess program effectiveness (delivery on objectives), impact (delivery on goals), efficiency (relationship of human and financial inputs to results), sustainability (likelihood of results and program persisting), and strategic design. | Information generated through M&E is regularly analysed and used to assess program performance (e.g., effectiveness, impact, efficiency, sustainability, and strategic design), and to inform any future phases. | Information generated through M&E is sometimes analysed and used to assess program performance (e.g., effectiveness, impact, efficiency, sustainability, and strategic design). | Information generated through M&E is rarely analysed and used to assess program performance. | Information generated through M&E is not analysed or used to assess program performance. | 4
Analysis and decisions documented in a format accessible to present and future staff. | Results of data/ information analysis is systematically documented in a format accessible to present and future staff and key partners. | Results of data/information analysis is sometimes documented in a format accessible to present and future staff and key partners. | Results of data/information analysis is rarely documented in a format accessible to present and future staff and key partners. | Results of data/information analysis is not documented in a format accessible to present and future staff and key partners. | 1
4C. Adapt Strategic Plan
The program is adapted systematically based upon analysis, and defined processes and evidenced in documenation such as the strategic, action, monitoring, operations plans. | Adaptive management is taking place and is documented. The theory of change, assumptions and learning/research questions are reviewed and are informing adaptive management practices. M&E information guides decision-making regarding strategy, tactics and any future phases of program. Staff regularly meet and share experiences and key lessons. | The program team sometimes uses monitoring data to support decision making and adaptive management, and decisions are documented. Change can be shown relative to the baseline. Staff regularly meet and share experiences and key lessons. | The program team rarely uses monitoring data to support decision making and adapt strategies. Analysis of progress towards objectives and goals tends to be subjective, very little evidence to back up claims. Staff sometimes involved in analysis and distillation of key lessons. | No systematic analysis of progress towards objectives and goals (only activities are tracked). Staff are not invited to analyse and share lessons. Limited evidence that activities are adapted in response to analysis of monitoring data. | 1
5. CAPTURE & SHARE LEARNING
5A/B. Document Learning
Key results and lessons regularly prioritized, documented, and shared. | Reflection in the program team and with stakeholders regularly takes place. Learning and lessons are regularly collected, documented, and communicated with key internal and external audiences (including partners, stakeholders) via appropriate and accessible means. Evidence and learning from the program regularly inform strategy and execution. | Program team sometimes reflects together. Some effort is made to document and share learning and lessons learned. Some effort is made to reflect and support a learning culture. Evidence and learning sometimes informs strategy and execution. | Ad-hoc effort is made to document and share lessons learned. Ad-hoc effort is made to contribute to a learning culture but little evidence is collected to understand what is working and not working with regards to learning and sharing. | Lessons and evidence not well documented or captured for dissemination. Lessons are not shared beyond the team. | 2
5C. Create a Learning Environment
Regular feedback shared formally or informally. | Individuals, teams, and the organization regularly reflect and seek and provide both formal and informal feedback from internal and outside sources. | Individuals, teams, and the organization sometimes reflect and seek and provide formal and/or informal feedback from internal and/or outside sources. | Individuals, teams, and the organization rarely reflect and seek and provide formal and/or informal feedback from internal and/or outside sources. | Individuals, teams, and the organization do not reflect or seek/provide formal and/or informal feedback from internal and/or outside sources. | 3
A safe environment and regular practices exist that encourage learning, innovation, questioning, and sharing failures as well as successes internally and externally. | Learning, innovation, questioning, and sharing frequently occur throughout the program life cycle as a result of staff perception that the work environment is a safe and encouraging space to do so. | Learning, innovation, questioning, and sharing often occur as a result of staff perception that the work environment is a fairly safe and encouraging space to do so. | Learning, innovation, questioning, and sharing rarely occurs due to staff perception that the work environment is not safe or encouraging to do so. | Learning, innovation, questioning, and sharing are not occurring due to staff perception that the work environment is not safe or encouraging to do so. | 4

## REPORT
AUDIT REPORT FOR: | 0 |  | AUDIT DATE: | 0
PROGRAM: | 0
Average Ratings by OS Sub-step (do not edit -- auto-generated) |  | Management Response (to be completed by program team)
OS Step and Sub-step | Avg. | What if anything will the program team do to improve this factor in the coming 1-2 years? | By what date will improvements be made? | Who has primary responsibility?
1. CONCEPTUALIZE
1A. Planning Purpose & Project Team | 3
1B. Scope, Vision & Conservation Targets | 2.8333
1C. Critical Threats | 1
1D. Conservation Situation | 3
2. PLAN ACTIONS & MONITORING
2A. Formal Action Plan | 2.1667
2B. Formal Monitoring Plan | 2.5
2C. Operational Plan | 2.6
3. IMPLEMENT ACTIONS & MONITORING
3A. Short-Term Work Plan & Timeline | 4
3B. Project Budget | 2
3C. Implement Plans | 2.3333
4. ANALYZE, USE, ADAPT
4A. Prepare Data for Analysis | 3
4B. Analyze Results | 2.5
4C. Adapt Strategic Plan | 1
5. CAPTURE & SHARE LEARNING
5A/B. Document Learning | 2
5C. Create a Learning Environment | 3.5
Improvement Needed
Minimal
Some
Significant
Major

## SUPPORTING GUIDANCE
TABLE OF CONTENTS FOR SUPPORTING GUIDANCE
The following worksheets contain guidance in support of a conservation audit. Reviewing and using this guidance is not be necessary in all cases but may be helpful to carrying out a successful audit process.
Click here to jump to the Whether to Audit worksheet.
Click here to jump to the Type of Audit worksheet.
Click here to jump to the Audit Process worksheet.
Click here to jump to information on audits vs evaluations vs learning
Click here to jump to guidance on using this audit tool for organizational scale audits.
Click here to jump to guidance on using this audit tool for thematic programs.

## Whether to Audit
DECIDING WHETHER TO DO A CONSERVATION AUDIT
Benefits of doing a conservation audit
Multiple parties benefit from a well executed conservation audit. First and foremost, the assessment process itself and its “deliverables” (e.g. report) assist the program and its team. Findings and recommendations that stem from a thorough conservation audit provide impartial and valuable feedback on program design including many aspects of planning, selected strategies, and execution. The transparent nature of the audit process and its reporting also can benefit conservation programs, partners and organizations by demonstrating the credibility of best practice and related results to funders, more distant actors, and the public.
Depending on its status and progress in the adaptive management cycle, a conservation program can profit in various ways from different types of audit. Conservation programs with rigorous planning and management in accordance with the best practice standards will have their successes highlighted by a conservation audit; those requiring improvements in their adaptive management processes will receive explicit recommendations to help them improve. Demonstration of adoption of those recommendations to improve program design and management can help to increase confidence in the program and its potential results, both internally and externally.
Finally, as more conservation audits are conducted, a larger network of lessons can be established and shared across the conservation community. Box 1 below provides a summary of costs and benefits from earlier experiences undertaking conservation audits.
What a conservation audit will not provide
A conservation audit is a particular type of analysis involving the review of the design and management of a program against industry-standard or organizational best practice guidelines. As such, unless additional questions, methods and clarifications of objectives are appended to an audit approach, a conservation audit will not provide, or be:
✗ A financial or administrative review,
✗ An assessment of the sufficiency or performance of existing human resources,
✗ A regulatory or "policing" analysis,
✗ A graded examination or test; and
✗ An evaluation.
Regarding evaluations, conservation audits and evaluations initially seem like very similar processes, however understanding the distinctions is important. Evaluations of conservation programs tend to focus on the extent to which programs achieve their specific goals and objectives and key factors affecting performance. Evaluation criteria typically include: strategic relevance and design, effectiveness, efficiency, impact and sustainability. Conservation audits, on the other hand, focus on how well projects adhere to a set of overall, established standards for planning, implementation, monitoring and evaluation (M&E), and adaptive management. Because M&E is a key component of best practice standards, conservation audits are not blind to project results, In fact, a conservation audit can lend credibility to reported results by assessing the context and process through which the results were generated and reported. In short, the relationship between process and impacts is a key focus of good conservation program evaluations and of conservation audits, yet the emphasis is placed more strongly on results for the former and on processes in the latter. The worksheet, Audits v Evals v Learning provides additional information on differences between audits and evaluations.
Deciding whether to do an audit
Deciding what, whether, and how to audit deserves attention so that ownership of the audit results is well established, clear, and the implications of the audit are taken seriously. The questionnaire and table of costs and benefits below provide some ways to consider whether to pursue a conservation audit. In the questionnaire, if you answer NO or MAYBE to a couple of questions or more, then a conservation audit would be highly recommended. This decision tool can be complemented by consideration of the costs and benefits identified from previous audits in the table below.
Simple questionnaire to help decide whether to do a conservation audit | YES | NO | MAYBE | REMARKS
1. Are you confident that the program is following "best practice" or applying standards to design and management?
2. Are you confident that the program is using adaptive management for decision making?
3. Are you confident that there are adequate resources (staff, money) available for excellence in program planning and management?
4. Have any other assessments been undertaken and/or is there any type of evaluative culture or quality improvement processes actively engaged?
5. Are you confident that the benefits of conservation auditing outweigh the costs (see Box 1 below)
BOX 1. Costs and benefits of conservation audits (as identified by audit and project team members) (from O’Neill 2007) | Costs |  |  | Benefits
Per team members of projects audited in the past. | Time |  |  | Improved strategic focus and goals
| Opportunity cost |  |  | Peer interaction and exchange
| Stress |  |  | Fresh, outside perspective
| Moderate costs to support logistics of audit |  |  | Opportunity to “step back” and reflect, focus on the big picture
Ideas on how to better integrate with partners
Increased visibility within organization
Forced succinct articulation and communication of project.
Identification of strengths and weakness in project design
Education of staff regarding institutional framework
Increased awareness by key senior staff
Per members of teams that have conducted past audits. | Time |  |  | Opportunity to reflect and gain perspective on own project
| Opportunity cost |  |  | Interaction, exchange, and networking with peers (audit and project teams)
| Stress, frustration, feeling of being overworked |  |  | Improved knowledge of, and/or appreciation for institutional standards
| Local travel |  |  | Increased understanding of constraints faced by projects outside of the US
Opportunity to see another project or region
Increased knowledge of host organization
Opportunity to use knowledge to assist another project
New perspectives on how to address conservation issues
Opportunity to participate in process of self-examination
Notes and Tips
1. A "lite" audit could be considered under the following conditions: 1) the program is in the early stages of conceptualization but building on other work having been done in the same geographic or thematic area or with some of the same stakeholders, 2) you want to carry out a quick review of the quality of a program's design and adaptive management practice, 3) your organization wants to quickly and lightly check on process and practice across all its programs once or twice a year to seek out patterns, successes and gaps, and 4) there is insufficient support or resources for an audit yet the program team are convinced it would yield useful information. The rigor or breadth of an audit is dictated primarily by the extent and quality of evidence used to support the audit, so a "lite audit" is achieved simply by gathering and utilizing less data/information/inputs.
2. If you want to audit against parts of the cycle instead of all the steps, it's easy, just use the section of the tool that provides the detail that you need. Before deciding to single out parts of the cycle, perhaps use a "lite" audit to make sure that the "selective" auditing you will pursue answers your questions and concerns. Also keep in mind that auditing the whole cycle can provide insights into areas of successful practice which is equally important to identifying steps that may need additional work. For additional support in conducting a lite audit exercise, please write to audits@conservationmeasures.org.
3. The audit framework and tool can be useful as a learning and information sharing framework by bringing groups of stakeholders or other actors to review and develop a shared understanding of the processes and practices which can shape and influence conservation programs. It can also bring to light policies and principles that are important to, and/or binding for different stakeholders. The framework and tool introduces the importance of best practice and the importance of taking time, and conducting well, the processes that will likely define success or failure. It can also help organizations, funders, other partners to prioritize, adapt, and create their own "adaptation" of the best practice concepts that are included here so they are case specific and embraced by program participants.

## Type of Audit
DECIDING THE TYPE OF, AND WHO WILL CONDUCT, THE CONSERVATION AUDIT
The key to selecting the 'best fit' conservation audit approach is largely dictated by why an audit is needed. Ideally the audit objectives were determined with the help of the WHETHER TO AUDIT decision support tools found in the preceding worksheet. Other considerations to decide on the type and the who include: budget, availability of potential audit team members, ownership of results, and support and acceptance by senior management and donors. Regardless of who conducts the audit, the program (and its parent organization) must take ownership of the process, results and recommendations, or it may not be worth doing. Also regardless of the type of audit, the basic steps outlined in the AUDIT TOOL AND INSTRUCTIONS are relevant. The table below can help you to decide on the type of audit to pursue, and who might conduct it. The table provides a brief description of different audit formats and "auditors," and outlines the principle benefits and drawbacks for each type.
BRIEF DESCRIPTION OF AUDIT TYPE AND WHO CONDUCTS | BENEFITS | DRAWBACKS
Self-Audits: Self-audits are conducted by the one or more members of the program team itself. These can be done at one's desk, via a meeting of a few hours, or through a workshop lasting one or more days. | ✓Cost effective ✓Regularity of audits and continual improvement ✓Ease of owning results ✓Shared responsibility and shared learning | ✗Focus is split between running the audit and participating in the audit ✗Self assessments tend to score higher ✗Outsiders may not consider the exercise independent/credible
Facilitated Self-Audits: Facilitated self-audits are conducted by the program team with the assistance of a facilitator who is knowledgeable in the Open Standards or the equivalent framework against which the audit will be conducted. The facilitator can be internal or external. These are in fact likely to be the most efficient and effective ways of auditing, as well as the best means to advance the practice of conservation auditing and adoption of the best practices laid out in the Open Standards within a program or organization. | ✓Cost effective ✓Regularity of audits ✓Ease of ownership of results ✓Cultivates capacity of the program team in the Open Standards (or equivalent) ✓Trained facilitator to organize and keep things on track so team can fully participate | ✗Facilitator could take over the process or not be the right person ✗Could be some cost depending on where the facilitator comes from ✗Program team could lose interest because of someone else leading ✗Outsiders may not consider the exercise fully independent/credible
Peer Audits: Also known as a “peer-review” conservation audit, the audit is conducted by a team of persons outside the program team, and often includes individuals from outside the organization running the program. Members of a peer-review audit team should be independent of the program team and its management structure and ideally including include experts who are familiar with the program's particular context, focal strategies, situational challenges and stakeholders, etc.. | ✓Particularly valuable when audit objectives include shared learning ✓Considered independent and external ✓Brings in different perspectives and objectivity, and so may be viewed as more credible | ✗More complicated to organize ✗Increased costs ✗Less program team intensive involvement and therefore learning/buy-in ✗Tends to involves "experts" vs. "auditors" ✗Peers may access confidential information
Externally Contracted Audit: Conservation audits undertaken by an external individual or team are considered independent. These types of audit are particularly useful when an objective external perspective is required, and when the process needs to have "increased" verification, transparency and credibility. | ✓Provides an external, independent perspective ✓Increases verification and confidence of results by donors and management ✓Useful when stakeholders or other partners are involved ✓Could contribute to capacity building of the program team | ✗Increased costs ✗Must carefully select the right auditor to meet needs ✗External auditor must familiarize self with the program ✗Increased logistics and organization ✗Increased "fear" factor within program team
An Audit within an Evaluation: With increasing frequency, audit-like components or approaches are being included as components of an evaluation. This means that when a mid-term, terminal, or any formal/informal evaluation is conducted, some or all of the criteria (or questions) used in conservation audits would be included in the evaluation framework. Most commonly, these audit criteria are included within the typical evaluation criteria of relevance and design and adaptive management/capacity, but they also can be included in evaluative analyses of efficiency and sustainability (also typical evaluation criteria). Like conservation audits, evaluative exercises can be conducted via self-assessments, facilitated self-assessments, and externally contracted analyses. | ✓Reinforces evaluative culture and the importance of and connection between audits and evaluations ✓Get the benefits from both processes under one effort ✓May appeal to senior management or donors as answer more questions | ✗Increased time needed (and potentially cost) ✗Evaluative questions can supersede process and practice (i.e., audit) ones | Click here to jump to additional guidance on the difference between conservation audits and evaluations.

## Audit Process
AUDIT PROCESS STEPS
Presented below is a recommended process to prepare for, conduct, and follow up on a conservation audit. As indicated earlier in these guidelines, however, each conservation audit will be somewhat different, depending on objectives and approach. Represented below is a fairly rigorous process that could require a few months total for preparation, data analysis, write-up, and concluding an audit. Realistically, however, it is also possible to conduct a worthwhile conservation audit within a few hours, a day, or a workshop of a few days, using best available information. Regardless of the time taken to do the audit, the steps presented below generally will be relevant. Ultimately, it is more important to conduct a quick and imperfect conservation audit on a regular basis than a perfect audit but very rarely.
Preparing for a Conservation Audit
It is important to take sufficient time to prepare for a conservation program audit so that the entire process (beginning to end) is clear and shared with appropriate people. Assuring that the program team and partners, the home organization and the "audit team" are adequately versed in the Open Standards (or organizational equivalent), and in the tools and approaches to be used during the audit, as well as in the type of results to expect from an audit (this may include differentiating audits from evaluations) will go a long way in creating the right atmosphere, participation, and ownership of the findings and recommendations.
STEP | TASKS
Selection | Use decision tools/tables as presented in the Whether to audit worksheet to decide if an audit is the right tool given needs/objectives and how the program would benefit. | Click here to jump to the Whether to Audit worksheet.
Set a few key objectives for the conservation audit (see Whether to audit section).
| Decide on the approach to the audit, who will lead and conduct the exercise (see alternatives in Type of audit worksheet), and when the audit will be conducted. | Click here to jump to the Type of Audit worksheet.
Scoping | Develop scope of the program audit either with or led by the program team.
Create a Terms of Reference (ToR) for the audit that include: what is being audited, who will be participating in the audit, who the audience for the audit is, the timeline for the audit, and the budget required.
Develop a list of resources needed (people, materials, funding) and send out information and requests.
Audit "Team" | Depending on "who" is undertaking the audit, begin contracting or other procedures to confirm responsibilities (e.g., a facilitator, program team, peers, external consultants, etc.).
Familiarize the program team and partners with the Open Standards (or appropriate framework), any tools to be used during the audit, and share the ToR.
Resources, Logistics and Methodology | Create a calendar and make any logistical arrangements, making sure that personnel and other key informants or stakeholders are lined up to participate.
Gather relevant documentation and data. At a minimum, this will include program strategy documents, monitoring and evaluation platforms and data, operational plans, action and work plans, and learning products.
Share gathered documents and data with the audit "team" and the program team. If using external assistance (e.g., a contractor or a peer audit), share the qualifications of the externals with the program team.
Hold an audit team briefing to confirm approach, work plan, logistics, and timeline for the audit.
Conducting a Conservation Audit
As with a financial audit, a conservation audit involves first and foremost gathering and consulting best available data and information to make an objective assessment of whether best design and management practices are being followed. As indicated above, performing this assessment can take anywhere from a couple of hours to several days, depending up on the approach being followed. Regardless, to ensure buy-in to audit process and findings, the steps below start and finish with consultation of the program team itself. The auditor(s) also should seek to documents findings fully, including justifications for ratings, as that information will be necessary to help the program team to decide what to improve and how.
STEP | TASKS
Kick-off | Ensure all involved understand the purpose, framework and methods, audience(s), and process for the audit, including roles and responsibilities of all involved. Update the TOR if needed.
Confirm expectations and planned outcomes.
If the process will involve site visits, interviews, etc., confirm all schedules and logistics.
Conduct The Audit | Conduct interviews (internal or external), surveys, site visits as process has defined.
Review/analyze all necessary information (e.g., from document review, internal and external interviews, etc.).
Complete the AUDIT SUBJECT and AUDIT TOOL Worksheets. Complete the rating and rating justification for each step and criterion. The audited program likely will derive greater value from the justification than from the rating.
Draft Preliminary Findings & Recommendations | Before concluding the audit exercise, summarize the findings of the audit and draft corresponding recommendations on how to improve the design and management of the audited program.
Clearly link recommendations to the conservation audit findings and organize them in order of priority.
Check Facts and Solicit Feedback | Summarize and discuss the preliminary findings and recommendations with the program team (ideally in person, but also can be done virtually).
Correct any factual errors and misinterpretations, and identify additional data or sources of information that may be helpful in filling in any gaps.
Edit the preliminary findings and recommendations as appropriate, based on the discussion, while striving to maintain the objectivity/independence of the analysis.
Solicit feedback on the conservation audit process itself.
Concluding and Following Up on a Conservation Audit
Any analysis, whether a conservation audit, financial audit, general review, or evaluation, will only be valuable insomuch as its findings are used to support improvement. Consolidating audit findings in a usable format, supporting the development of a management response, and following up at periodic intervals are therefore vital to ensuring that the conservation audit leads to strengthening program design and management. Often, however, follow up tends to fall by the wayside and so we suggest that the auditor(s) and/or program team formally schedule follow-up activities, including dates for reviewing management response implementation and performing repeat audits.
STEP | TASKS
Draft the Report | Write up the preliminary findings and recommendations into a concise draft report that is structured in a manner consistent with the audit framework in the AUDIT TOOL.
Share the draft report with the program team and other relevant individuals (e.g., senior management, key partners) and request written feedback.
After receiving the feedback, complete the final written report. Again, feedback from the project team is important, but does not guarantee any changes in the report.
Prepare Program Team’s Management Response | Based on the findings and recommendations, the program team and other responsible parties draft a management response that outlines how program design and management will change as a result of the audit. The response should include specific actions, timing, roles and responsibilities.
Follow-up, Capture Learning, Repeat | Capture and communicate the findings, recommendations, and broader learning from the audit to relevant audiences, including lessons learned about the Open Standards-based project planning and management process, and lessons regarding the audit process itself.
Every six months, review progress on implementing the actions laid out in the management response.
Compile and submit to CMP any findings that could be incorporated into the “Guidance” sections of further iterations of the Conservation Audit Protocol, including tools used, process tips, report formats, etc.
Consider repeating audits every few years, particularly of high-profile, high-risk, and/or high-cost programs.

## Audits v Evals v Learning
AUDITING VERSUS EVALUATION VERSUS ORGANIZATIONAL LEARNING
In the strictest sense, Conservation Auditing can only answer key learning questions related to the processes of program design and adaptive management. Only Conservation Evaluation can contribute to answering questions related to “What is working and what isn’t and why?” Learning Analyses gather information from multiple projects or programs to answer key questions with broader impact on organizational effectiveness.
Tool | Definition | Primary Questions Answered | Examples of Learning Questions | Data/Info Needed
Conservation Audit | A review of the processes of planning and execution of a conservation project or program. | Has the project/program set itself up for success by following best practices for planning and management? Are our reported results credible? Is the project/program being run in a manner that will support organizational learning? | What approaches have been used to support planning efforts at different scales? How have projects/programs tackled the need to gather and utilize monitoring data? How does it carry out the “E” of “M&E”? Which components of the standards typically are or are not adopted? Why/why not? | Anecdotal, qualitative Program documents Gathered annually or longer periodicity Audit reports
Conservation Evaluation | A review of the design, effectiveness, impact, efficiency, and sustainability of a conservation project or program. Every evaluation should include a conservation audit component. | Is the project/program successful? Why/why not? What can be done to improve and align delivery? Is the program well aligned with the internal and external priorities? Are program goals being achieved? Why/why not? Are results being achieved in a timely and efficient manner? Are project/program impacts likely to persist? | What approaches have brought about positive changes in target status or key factors? What approaches successfully engaged key stakeholders? How has the project/program tackled ‘persistence’ issues like long-term financing; legal/policy framework development; and capacity building of key programs, agencies, and civil society? | Regularly collected and documented data/info Quantitative and/or systematically gathered monitoring data preferred Can be anecdotal/ qualitative info collected retroactively, but must pay attention to issues of causality and attribution Most robust if conducted on projects/programs where there is a system of regular monitoring, evaluation, and adaptation in place.
Organizational Learning Analysis | Analyses intended to consolidate ‘lessons learned’ regarding impact/efficiency of certain types of conservation actions, aspects of design or implementation, etc. | Across our efforts, what’s “working” and what’s not and under what conditions or circumstances? In the future, what should we do and what should we avoid to improve impact and efficiency? | What are pitfalls to avoid when starting up large-scale conservation interventions? What are successful techniques for engaging large corporations in supporting and taking conservation action? Does adoption of full cycle adaptive management improve conservation effectiveness?

## Auditing Orgs
CONSERVATION AUDITING AT ORGANIZATIONAL SCALE
Over the years, CMP and its members have employed various methods to assess the extent to which whole organizations are adhering to the best practices outlined in the Open Standards (or equivalent organizational frameworks). These experiences have shown that this is more practically done for smaller organizations, where the practices of programs are well known at the central level, but is more challenging to do for larger organizations that can have many hundreds of programs distributed around the globe. While attempts have been made in the past to simply carry out an audit on an organization without looking to the practices of specific programs, this is not recommended, particularly for larger, globally distributed organizations. Based upon past experience, it is not possible for a single, centrally-located informant to speak to the entirety of a large and complex organization, such as WWF, TNC, CI or WCS.
Consequently, based upon these efforts, we recommend that to devise a conservation audit analysis at the organizational scale, any organization--small or large--undertake the steps laid out below. We note that those organizations wishing to go beyond this basic framework for organizational conservation auditing may want to consider The Performance Imperative: A framework for social sector excellence (https://leapambassadors.org/products/performance-imperative/) and Open Standards support for business performance and reporting (http://cmp-openstandards.org/wp-content/uploads/2018/04/Position-OS-within-business-performance-and-reporting-frameworks.pdf).
To carry out a conservation audit at the organizational scale:
1) Conduct conservation audits of a representative sample of programs. In the case of smaller organizations, this might include nearly all programs. For larger organizations, we recommend that this sample seek to include broad geographic representation, both place-based and thematic (e.g., targeting a particular contributing factor or issue) programs, smaller and larger programs, and ultimately capture a significant portion of the organization's annual operating budget. For network-type organizations like WWF, conducting audits within each office and sharing the results across the network could provide a picture of the organization as a whole. Effort should be made to carry out the audits following the common methodology presented in this tool, and ideally via a single facilitator who can ensure consistency in interpretation and application of the tool.
2) Aggregate or assemble program-level results. To develop an overall sense of the extent to which an organization is adhering to best design and management practice, aggregate the results from across the conservation audits of the representative set of programs. This should highlight where practice is consistently strong, weak, or variable. Although CMP hopes in future to develop a recommended method for aggregating the results of multiple program audits to support an organizational assessment, such an approach does not yet exist; it will be up to each organization to determine how best to do this.
3) Complement the program-scale audits by completing the organizational-scale audit assessment below.
Audit Question | Rating: No/Mostly No Somewhat No Somewhat Yes Yes/Mostly Yes | Justification for Your Answer
Does your organization have a robust planning and management framework and accompanying set of standards (i.e., they support well-grounded design, clear theories of change, monitoring and evaluating based on theories of change, and adaptation based on results of evaluation and lessons learned)? | Somewhat Yes
Does your organization have supporting principles and policies for the above planning and management framework and standards? | Yes/Mostly Yes
Does your organization provide adequate financial resources to implement to a high standard the planning and management framework at all appropriate scales and locations? | Somewhat No
Does your organization provide adequate human resources to implement to a high standard the planning and management framework at all appropriate scales and locations? | Somewhat No
Does your organization have induction and capacity building programs in place that ensure both headquarters and distributed staff are oriented to and know how to apply the organizational planning and management frameworks? | Somewhat Yes
Does your organization have supporting IT, data analysis and communication mechanisms in place as needed to ensure effective application of organizational planning and management frameworks? | No/Mostly No
Does your organization practice systematic, evidence-based adaptive management such that it is in evidence within the governance practices guiding central management or headquarters structure? | No/Mostly No
Does your organization have an underlying culture in place that promotes and supports evaluative thinking and ongoing learning culture such that regular improvement is encouraged (even through identification and discussion of "failures" or efforts that didn't go as hoped/planned)? | No/Mostly No

## Auditing Thematic
SOME ADDITIONAL GUIDANCE FOR AUDIT TOOL USE WITH THEMATIC PROGRAMS
The audit tool, framework and guidance are useful for any type of program or project. Examples of thematic programs using the OS are plentiful, and Version 1.0 of the audit tool was used for at least one thematic program audit- the WWF Marcoeconomics Program. Furthermore, tools and guidance to help thematic programs "take the leap" into the OS can be found at http://cmp-openstandards.org/using-os/guidance/.
The most important guidance for adapting the audit tool to different types and scales of programs is to be pragmatic, and match the tool criteria to the design and management practices that make the parameters of your program clear. It is also possible to skip certain criteria that don’t apply to your program, though be wary of doing this as all the criteria in one form or the other are useful, and are considered conservation industry best practice standards. The term thematic in this context includes, but is not limited to,: policy, footprint, threat-based, actor-based or human well being–based programs
The OS steps and corresponding audit tool criteria are designed to be adaptable, we provide a table below that takes you through the program cycle and points to certain steps or areas which either need no adaptation or change, or where some different thinking and criteria may be helpful. Most steps and criteria are easy to follow and to change, if necessary, to any situation and program type. For additional assistance with conducting an audit of a thematic program, please write to audits@conservationmeasures.org.
Table of considerations, adaptations or changes for use of the conservation audit tool for thematic programs
OS Step in Audit Tool | Recommendations
1. CONCEPTUALIZE
1a. Planning Purpose/program team | No change needed
1b. Scope, Vision & Conservation Targets | Scope: No change needed although using 'problem definition tools' may help to define the scope. A program with non-biodiversity targets can, and probably should, have “maps” to better clarify the scope. Thematic programs (e.g. policy) may need maps linking policy connections or policy centers, thematic or threat-based programs (e.g. Climate Change) may also need maps to support the links between specific targets of the program and the broader vision. "maps' (used in its broadest concept) may help clarify the extent of a threat, and the scope of human well being orientations. Maps may also hel emphasize linkages and/or geographic scopes. It is important to think outside the box when consider what type of map might help clarify the scope, e.g. process maps can be useful under certain circumstances. Vision: No change needed Targets: Typically thematic programs CONTRIBUTE to higher level biodiversity or nature/natural systems targets or goals. Be sure to consider these so that you can make appropriate linkages back to the desired future status at the highest level possible. These high level targets may come from your organization or an outside source, e.g. global marine goals and targets. Conservation thematic programs need to ensure that their targets are linked (even loosely) to nature in the Vision and/or to “higher-level” goals. Human Well-Being (HWB) Targets: In the context of biodiversity conservation programs, HWB targets should be supported by their connection to nature generally and/or biodiversity targets. One way this can be done is by clarifying the connection between the HWB target and nature through the lens of ecosystem services.
1c. Critical threats | For thematic programs, the concept of defining and prioritizing the critical threats may be useful as they could help focus in on the best strategies for actions, identify influential actors, understand whether there are compounding threats when explored together. It will be necessary to consider what aspect of direct threats are helpful to better understand the context in which your program is functioning in order to adapt this criteria. It could be that the thematic program is all about a critical threat, and thinking through how extensive it is or whether any critical threats are influenced by the main emphasis of the program, or how they shape the scope of the program will be helpful.
1d. Conservation Situation | Indirect threats & opportunities: Thematic programs often are designed around indirect threats and opportunities and it is important to define these well and understand relationships amongst them in order to help develop the theory of change. There is not a needed change in the audit tool criteria as having a good understanding of these will improve the quality of your design.
Stakeholders: No change necessary though important to focus on those with influence and power, the marginalized and institutions and processes that are involved.
Conceptual model: No change needed; a conceptual model is best practice for any type of program.
2. PLAN ACTIONS & MONITORING
2a. Formal Action Plan | Goal statements: for linking to biodviersity targets, look at statements or goals and possibily adopt these from those at portfolio, organizational or other level. For thematic or HWB targets, goals can be defined as "what success looks like".
Objectives: should define future state of indirect threats, opportunities, desired status of issues. No big changes.
Strategies: no change needed.
Theory of change and lesser objectives: No change needed.
Formal plan: No change to criteria
2b. Formal Monitoring Plan | All aspects of the tool and criteria are relevant to thematic programs. No change needed.
2c. Operational Plan | All aspects of the tool and criteria are relevant to thematic programs. No change needed.
3. IMPLEMENT ACTIONS & MONITORING
3a. Work plan | All aspects of the tool and criteria are relevant to thematic programs. No change needed.
3b. Budget | No change needed.
3c. Implement | No change needed.
4. ANALYZE, USE, ADAPT
All aspects of the tool and criteria are relevant to thematic programs. No change needed.
5. CAPTURE & SHARE
All aspects of the tool and criteria are relevant to thematic programs. No change needed.
NOTE
Often thematic programs focus on or are strongly influenced by a set of internal, and more importantly, external positions or policies that MUST be understood, taken on board and audited against. This is especially true when compliance to those policies/positions is crtiical for increased legitimacy.

## APPENDICES
APPENDICES
Acronyms
Glossary
References

## Acronyms
ACRONYMS
AWF | African Wildlife Foundation
CI | Conservation International
CCNet | Conservation Coaches Network
CMP | Conservation Measures Partnership
Evals | Evaluations
FOS | Foundations of Success
FTE | Full time Equivalent
HR | Human Resources
HWB | Human well being
IFAW | International Fund for Animal Welfare
JGI | Jane Goodall Institute
M&E, ME | Monitoring and Evaluation
NB | Note Bene or Note well/Important to Note
NFWF | National Fish and Wildlife Foundation
NGO | Non Government Organization
OS | Open Standards for the Practice of Conservation
ToR | Terms of Reference
TNC | The Nature Conservancy
UK | United Kingdom
US | United States
USAID | United States Agency for International Development
USFWS | United States Fish and Wildlife Service
WCS | Wildlife Conservation Society
WWF | World Wide Fund for Nature or World Wildlife Fund

## Glossary
GLOSSARY AND CRITERIA OF KEY TERMS AND CONCEPTS
Adaptive management - The incorporation of a formal learning process into conservation action. Specifically, it is the integration of program design, management, and monitoring to provide a framework which aids in the systematic testing of assumptions. It promotes learning and supplies timely information for management decisions; it is not a trial and error approach.
Assumption - An assumption in program adaptive management is a factor considered to be true, real or certain often without evidence, proof or demonstration. An implicit assumption is one that includes the underlying thinking made in the development of a theory of change, results chain, course of action, decision, or judgment that are not explicitly voiced nor necessarily understood by those making decisions.
Audit - An assessment of a program with respect to its application of industry agreed standards, or best practices.
Contributing Factors - The ultimate factors, usually social, economic, political, institutional, or cultural, that enable or otherwise add to the occurrence or persistence of proximate direct threats. There is typically a chain of contributing factors behind any given direct threat. In a situation analysis, these factors are often subdivided into indirect threats (factors with a negative effect, such as market demand for fish) and opportunities (factors with a positive effect, such as a country’s land-use planning system that favors conservation). Contributing factors are synonymous with key or underlying factors, indirect threats, drivers, or root causes.
Direct Threat - The proximate human activities or processes that have caused, are causing, or may cause the destruction, degradation, and/or impairment of biodiversity targets (e.g., unsustainable fishing or logging). Direct threats are synonymous with sources of stress and proximate pressures. Threats can be past (historical), ongoing, and/or likely to occur in the future. Natural phenomena are also regarded as direct threats in some situations.
Evaluation - An assessment or review of a program in relation to its own previously stated goals and objectives, and typically using all or some of the following criteria: relevance and design, efficiency, effectiveness, impact, sustainability and adaptive capacity as a framework for the assessment.
Footprint - The ecological footprint is the impact of a person, community, country, industry etc. on the environment expressed or measures as the amount (or area) of land and water required to produce the goods consumed and to assimilate the waste produced.
Goal - A formal statement detailing a desired impact of a project such as the desired future status of a target. A good goal should be: linked directly to one or more conservation targets; impact oriented by representing the desired future status of the conservation target over the long term; measurable in relation to some standard scale (numbers, percentage, fractions, or all/nothing states); time limited, generally 10 or more years; and specific such that it is clearly defined so that all people involved in the project have the same understanding of what the terms in the goal mean.
Impact - The desired future state of a conservation target. A goal states the desired impact.
Indicator - A measurable entity related to a specific information need such as the status of a target, change in a threat, or progress toward an objective. A good indicator is one that is: measurable – able to be recorded and analyzed in quantitative and qualitative terms; precise − defined the same way by all people; consistent – not changing over time so that it always measures the same thing; and sensitive – changes proportionately in response to the actual changes in the condition being measured.
Indirect threats - see Contributing Factors.
Logframe or Logical framework - A planning tool consisting of a matrix which provides an overview of a project's goal, activities and anticipated results. It provides a structure to help specify the components of a project and its activities and for relating them to one another.
Method - A specific technique used to collect data to measure an indicator. A good method is: accurate – the data collection method has little or no margin of error; reliable − the results are consistently repeatable - each time that the method is used it produces the same result; cost-effective – it does not cost too much in relation to the data it produces and the resources available; feasible in that it can be implemented by people on the project team; and appropriate such that it fits within site-specific cultural, social, and biological norms.
Monitoring - The periodic collection and evaluation of data relative to stated program goals and objectives (also referred to as monitoring and evaluation (abbreviated M&E).
Nested or Associated Targets - Those targets which benefit from the conservation of selected targets by association.
Objective - A formal statement detailing a desired outcome of a program such as reducing a critical threat. A good objective meets the criteria of being: results oriented, measurable, time limited, specific, relevant, and practical. If the program is well conceptualized and designed, realization of a it’s objectives should lead to the fulfilment of stated goals and ultimately its vision.
Outcome - The desired future state of a threat or opportunity factor. An objective is a formal statement of the desired outcome.
Process - or Business Process, a collection of related, structured activities that produce a specific service or product (serve a particular goal); "Processes are the behaviors of real people and events – not documents!"
Program - A group of projects which together aim to achieve a common broad vision. Can also be used for a single project or portfolio, and is often interchangeable with project.
Project - A set of actions undertaken by a defined group of practitioners to achieve defined goals and objectives. The basic unit of conservation work.
Portfolio - A high-level grouping of projects and programs, managed together to achieve a strategic objective; portfolio management aims to focus resources on the right projects and programs.
Rate - A measure, quantity, or frequency, typically one measured against another quantity or measure
Result - The desired future state of a target. Results include impacts which are linked to targets and outcomes which are linked to threats and opportunities.
Results-Chain - A graphical depiction of a project’s core assumption, the logical sequence linking project strategies to one or more targets. In scientific terms, it lays out hypothesized relationships.
Stakeholder and Stakeholder Analysis - A “stakeholder” can be defined as: Any individual, group, or institution who has a vested interest in the natural resources of the project area and/or who potentially will be affected by project activities and have something to gain or lose if conditions change or stay the same. Stakeholders are all those who need to be considered in achieving project goals and whose participation and support are crucial to its success. Stakeholder analysis identifies all primary and secondary stakeholders who have a vested interest in the issues with which the project or policy is concerned. The goal of stakeholder analysis is to develop a strategic view of the human and institutional landscape, and the relationships between the different stakeholders and the issues they care about most.
Strategy - A group of actions with a common focus that work together to reduce threats, capitalize on opportunities, or restore natural systems. Strategies include one or more activities and are designed to achieve specific objectives and goals. They are typically linked directly to and affecting one or more critical factors; focused − outlining specific courses of action that need to be carried out; feasible in light of the project’s resources and constraints; and appropriate – acceptable to and fitting within site-specific cultural, social, and biological norms.
Target - An element of biodiversity at a project site, which can be a species, habitat, or ecological system that a project has chosen to focus on; can also be a human wellbeing target which, in the context of conservation projects, focus on those components of human wellbeing affected by the status of conservation targets.
Threats - see Direct Threats or Contributing Factors.
Theory of change - A planning methodology that defines goals and maps backwards to consider what needs to happen to realize them. It is essentially a comprehensive, and convincing, description of how and why a desired change is expected to happen in a particular context.
Vision Statement - A general statement of the desired state or ultimate condition that a project is working to achieve. A good vision statement should be: relatively general so broadly defined to encompass all project activities; visionary − Inspirational in outlining the desired change in the state of the targets; and brief, simple and succinct so that that all participants can remember it.

## References
REFERENCES
CMP 2006. Conservation Audit Protocol. The Conservation Measures Partnership. Draft Version 1.0. November 2006.
CMP 2013. The Open Standards for the Practice of Conservation. Version 3.0. Available from: www.openstandards.org.
Muir 2010. Are we measuring conservation effectiveness? A survey of current results-based management practices in the conservation community. Unpublished report. CMP.
O'Neill 2007. Conservation Audits: Auditing the Conservation Process--Lessons Learned, 2003 – 2007. Prepared by Elizabeth O'Neill for the Conservation Measures Partnership. July 2007.
O'Neill et. al 2012. Resources for Implementing the WWF Project & Programme Standards: Step 5.3--Evaluation Guidelines (with TOR outline). November 2012.
Redford et. al 2014. Summative Evaluation of Conservation Measures Partnership and Conservation Coaches Network to Strengthen Results-Based Management in Conservation. 2014. Kent H.Redford, M.W. Schwartz and K. Hulvey.
Stewart 2016. Conservation Capability Maturity Model: A model for assessing organisational performance and identifying potential improvements. Annette Stewart - Fulbright Scholarship 2016.
Stewart 2016. Open Standards support for business performance and reporting: Outlining a range of tools for improving performance and reporting of conservation organisations. Annette Stewart - Fulbright Scholarship 2016.
TNC 2005. TNC audit framework. TNC’s Conservation Audit Protocol. Version: DRAFT – June 2005
WWF 2005. WWF Conservation Programme Audit Tool.
WWF year unk. OS Self Assessment Tool. Link found under Step 5.3 here: http://wwf.panda.org/what_we_do/how_we_work/programme_standards/

## DO NOT EDIT
Rating Scale | Rating Scale
4 | No/Mostly No
3 | Somewhat No
2 | Somewhat Yes
1 | Yes/Mostly Yes
N/A
Format of Audit
Self-assessment
Facilitated self-assessment
Peer-led audit
External consultant(s)
Other